## Document List
| Project |  | : | J69P
| Part Number |  | : | 7176-9049
| Status |  | : | New Project
| M/P |  | : | August 2025
| OEM |  | : | Toyota
No. | APQP Stage |  |  |  | Document Level |  | Uploader | Approver | Validator | Target | Status Document | Document Progress | Main Due Date | Approver |  | Summary Progress
1 | Plan & Define Program | [11 empty] | 2025-07-01 |  |  | 100%
| 1. Drawing RFQ |  |  |  | 3 |  | Nadila | - | - | 2025-06-15 | TEMPORARY | 12.5% |  | Rizki
| 2. Drawing Review Result (DRR) |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  | 12.5% |  | Nadila
| 3. Investment Analysis |  |  |  | 4 |  | Nadila | Nadila | Nanang |  |  | 12.5% |  | Ruliyanto
| 4. RFQ Form Analysis |  |  |  | 4 |  | Nadila |  |  |  |  | 12.5% |  | La'ali
| 5. Kick off Order |  |  |  | 3 |  | Erlina | - | - |  |  | 12.5% |  | Selvia
| 6. Official Drawing & Technical Data |  |  |  | 1 |  | Nicky | - | - |  |  | 12.5% |  | Adnan K
| 7. Schedule Customer |  |  |  | 2 |  | Nicky | Nadila | Nanang |  |  | 12.5% |  | Wahyu J.
| 8. APQP Timeline |  |  |  | 2 |  | Nicky | - | - |  |  | 12.5% |  | Nanang
2 | Product Design & Development | [14 empty] | 10%
| 1. 3D/2D Drawing |  |  |  | 1 |  | Nicky | - | - |  |  |  |  | Rizki
| 2. Material Properties |  |  |  | 1 |  | Nicky | - | - |  |  | 6.67% |  | Arif
| 3. DFMEA Part |  |  |  | 4 |  | Nicky | Arif | Nanang |  |  |  |  | Nadila
| 4. Kakotora |  |  |  | 3 |  | Nicky | - | - |  |  |  |  | La'ali
| 5. Mold Specification |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | Bayu Saputri
| 6. Mold Design Review |  |  |  | 3 |  | Nicky | Rulli | Adnan |  |  |  |  | Ruliyanto
| 7. DFMEA Mold |  |  |  | 4 |  | Nicky | Arif | Nanang |  |  |  |  | Adnan K
| 8. Mold Schedule |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | Nanang
| 9. Part Inspection Standard (PIS) |  |  |  | 2 |  | Nicky | Nadila | Nanang
| 10. (Prototype) Flow Chart |  |  |  | 3 |  | Nicky | Nadila | Nanang
| 11. Child Part Data |  |  |  | 3 |  | Prisma | Nadila | Nanang
| 12. Mating Part List |  |  |  | 3 |  | Nicky | Nadila | -
| 13. Packing Specification Draft |  |  |  | 2 |  | Nicky | Rulli | Adnan
| 14. (Prototype) BOM |  |  |  | 3 |  | Nicky | Arif | Nanang
| 15. Balloned Drawing |  |  |  | 1 |  | Nicky | - | -
| 16. SOC Test Report |  |  |  | 3 |  | Prisma | La'ali | Wahyu J.
3 | Process Design & Development
| 1. Inspection Instruction (Check Point) |  |  |  | 3 |  | Joko | Rulli | Adnan |  |  |  |  | Rizki
| 2. Packing Specification & Evaluation |  |  |  | 2 |  | Nicky | Nadila | Nanang |  |  |  |  | Nadila
| 3. Instruction Packing |  |  |  | 3 |  | Yusuf | La'ali | Wahyu J. |  |  |  |  | Yakub
| 4. Working Instruction Subpacking Collar |  |  |  | 3 |  | Tian | Yakub | Nanang |  |  |  |  | La'ali
| 5. (Prototype) PFMEA |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | Ruliyanto
| 6. (Prototype) Control Plan |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | Adnan K
| 7. (Prototype) QCPC |  |  |  | 2 |  | Yusuf | La'ali | Wahyu J. |  |  |  |  | Wahyu J
| 8. Measurement Report (N1 Data) |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | Nanang
| 9. Shoken Submission |  |  |  | 3 |  | Nicky | Nadila | Nanang
4 | Product and Process Validation
| 1. Shoken Approval |  |  |  | 2 |  | Nicky | Nadila | Nanang |  |  |  |  | Rizki
| 2. Cpk / Ppk Data |  |  |  | 3 |  | Prisma | Rulli | Adnan |  |  |  |  | Nadila
| 3. Trial Status Record & Problem Follow Up Sheet |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | La'ali
| 4. Stock Before Mass Production Has Been Handled |  |  |  | 3 |  | Nicky | Yakub | Nanang |  |  |  |  | Ruliyanto
| 5. Working Instruction Assembly |  |  |  | 3 |  | Yusuf | La'ali | Wahyu J. |  |  |  |  | Adnan K
| 6. Injection Parameter Setting & Verification |  |  |  | 3 |  | Yusuf | La'ali | Wahyu J. |  |  |  |  | Wahyu J.
| 7. TSKK Injection |  |  |  | 3 |  | Yusuf | La'ali | Wahyu J. |  |  |  |  | Nanang
| 8. TSKK Assembly |  |  |  | 3 |  | Yusuf | La'ali | Wahyu J.
| 9. TSKK Final |  |  |  | 3 |  | Yusuf | La'ali | Wahyu J.
| 10. (Pre-launch) Process Flow Chart |  |  |  | 3 |  | Nicky | Nadila | Nanang
| 11. (Pre-launch) PFMEA |  |  |  | 3 |  | Nicky | Nadila | Nanang
| 12. (Pre-launch) Control Plan |  |  |  | 3 |  | Nicky | Nadila | Nanang
| 13. (Pre-launch) QCPC |  |  |  | 2 |  | Yusuf | La'ali | Wahyu J.
| 14. (Production) BOM |  |  |  | 3 |  | Nicky | Nadila | Nanang
| 15. MSA (Measurement System Analys) |  |  |  | 3 |  | Prisma | Rulli | Adnan
| 16. Dummy MO Verification |  |  |  | 3 |  | Wahyu H. | Nadila | Nadila
| 17. HVPT Report Injection |  |  |  | 1 |  | Joko | Rulli | Adnan
| 18. HVPT Report Assembly |  |  |  | 1 |  | Joko | Rulli | Adnan
| 19. HVPT Report Final |  |  |  | 1 |  | Joko | Rulli | Adnan
| 20. Limit Sample |  |  |  | 2 |  | Nicky | Nadila | Nanang
| 21. Buken Submission |  |  |  | 2 |  | Nicky | Nadila | Nanang
| 22. Buken Approval |  |  |  | 2 |  | Nicky | Nadila | Nanang
5 | Feedback, Assessment & Corrective Action
| 1. (Production) Process Flow Chart |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | Rizki
| 2. (Production) PFMEA |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | Nadila
| 3. (Production) Control Plan |  |  |  | 3 |  | Nicky | Nadila | Nanang |  |  |  |  | La'ali
| 4. (Production) QCPC |  |  |  | 2 |  | Yusuf | La'ali | Wahyu J. |  |  |  |  | Selvia
| 5. MTA Submission |  |  |  | 2 |  | Prisma | Nadila | Nadila |  |  |  |  | Adnan K
| 6. Quality Declaration |  |  |  | 3 |  | Prisma | Rulli | Adnan |  |  |  |  | Wahyu J.
| 7. PPAP Data Comparisson |  |  |  | 3 |  | Nicky | Rulli | Adnan |  |  |  |  | Nanang
| 8. PPAP Approval |  |  |  | 3 |  | Nadila | Rulli | Adnan
| 9. IPC Point (Initial Production Control) |  |  |  | 2 |  | Joko | Rulli | Adnan
| *Notes : | OPEN BERWARNA MERAH |  |  |  | Document Level 1 : OPEN-TEMPORARY-CLOSE | [8 empty] | DOC. CUSTOMER TIDAK PERLU APPROVAL/SIGN
| SUBMITTED BERWARNA HIJAU |  |  |  |  | Document Level 2 : OPEN-TEMPORARY-SUBMITTED-APPROVED | [8 empty] | DOC. CUSTOMER PERLU APPROVAL/SIGN CUST
| TEMPORARY BERWARNA ORANGE |  |  |  |  | Document Level 3 : OPEN-TEMPORARY-CLOSE | [8 empty] | DOC. INTERNAL TIDAK PERLU APPROVAL/SIGN CUST (APPROVAL INTERNAL ONLY)
| CLOSE BERWARNA BIRU |  |  |  |  | Document Level 4 : OPEN-SUBMITTED-APPROVED | [8 empty] | DOC. INTERNAL PERLU APPROVAL/SIGN CUST
APPROVED BERWARNA ABU-ABU
Search

## Document Tree
Request For Quotation
Investment Analysis
RFQ Form Analysis
Drawing Review Result (DRR)
APQP Timeline
Schedule Customer
Official Drawing & Technical Data
Kick off Order
STAGE 1
STAGE 2
Drawing RFQ
Investment Analysis
RFQ Form Analysis
Drawing Review Result (DRR)
APQP Timeline
Schedule Customer
Official Drawing & Technical Data
Kick off Order
Inspection Instruction
(Prototype) Control Plan
(Prototype) PFMEA
(Prototype) QCPC
STAGE 3
Cpk / Ppk Data
STAGE 4
STAGE 5
WI Subpacking Childpart
Instruction Packing
Packing Spec & Evaluation
Measurement Report (N1 Data)
Shoken Submission
WI Assembly
MSA (Measurement System Analys)
Dummy MO
TSKK
(Production) BOM
Shoken Approval
Parameter Setting & Verification
Control Stock Trial
Trial Status Record & Problem Follow Up Sheet
HVPT Report
Limit Sample
Buken Submission
Buken Approval
(Pre-launch) Control Plan
(Pre-launch) QCPC
(Pre-launch) PFMEA
(Pre-launch) Flow Chart
Mold Specification
Part Inspection Standard
(Prototype) BOM
DFMEA Mold
Ballooned Drawing
Packing Specification Draft
Mold Design Review
Mold Schedule
DFMEA Part
(Prototype) Flow Chart
Child Part Data
SOC Test Report
Kakotora
Mating Part List
Material Properties
3D/2D Drawing
Quality Declaration
MTA Submission
PPAP Data Comparisson
PPAP Approval
IPC
(Production) Control Plan
(Production) QCPC
(Production) PFMEA
(Production) Flow Chart